{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":33,"n_cols":9,"rows_kept":33,"merged":[[0,0,0,8],[32,0,34,8]]}
[" 2025年下半年 河源市中心城区城市道路挖掘计划"]
["序号","项目单位","工程名称","管线类型","具体施工区域","长度","施工期限","施工方式","备注"]
[1,"源城供电局","北郊所220kV河源站新出一回10kV线路与10kV中山甲线720、10kV中山丁线732环网工程","电力电缆","茶山公园、新江路、丽日","300米","2025-7-1-\n2025-9-30","顶管+排管"]
[3,"源城供电局","北郊所220kV河源站新出一回10kV线路与10kV红星西线739、10kV中山乙线711环网工程","电力电缆","丽日广场北侧至丽日路对面，再沿河源大道往北至红星西路，再沿红星西路至东华路路口","450米","2025-7-1-\n2025-9-30","顶管+排管"]
[4,"源城供电局","北郊所新建10kV永康甲线733东城中片区#7公变台区工程","电力电缆","黄沙安置点内部路","100米","2025-5-15-2025-7-30","排管"]
[5,"源城供电局","南郊所110kV双下站新出一回10kV线路与10kV双石线709、10kV城西线741、10kV南门乙线704环网工程","电力电缆","河中路，河源大道，双下路","200米","2025-5-1-\n2025-12-30","顶管+排管"]
[6,"源城供电局","北郊所110kV黄沙变电站10kV中山丙线722改造工程","电力电缆","建设大道（东华路段至新风南路段）","143米","2025-8-15-\n2025-12-30","排管"]
[7,"源城供电局","北郊所新建10kV新院丙线711东城西二片区#6公变台区工程","电力电缆","永盛路（文昌路至盛源路段）","319米","2025-8-15-\n2025-12-30","顶管+排管"]
[8,"源城供电局","南郊所110kV城南变电站10kV公园线714线路改造工程","电力电缆","公园西路（公园东路至鸣凤路段）","230米","2025-9-1-\n2025-12-30","顶管+排管"]
[9,"河源市水业集团发展有限公司","分区安装流量计工程","给水","建设大道（东华路至中山大道路段）","5米","2025年7月18日-7月30日","开挖"]
[10,"河源市水业集团发展有限公司","分区安装流量计工程","给水","红星路（东华路至中山大道路段）","5米","2025年6月29日-7月13日","开挖"]
[11,"河源市水业集团发展有限公司","分区安装流量计工程","给水","益民街与中山大道交汇处中间绿化带（往珠河大桥方向10米左右）","5米","2025年7月25日-8月10日","开挖"]
[12,"河源市水业集团发展有限公司","分区安装流量计工程","给水","长安街（中山大道至文昌路段）","5米","2025年8月10日-8月25日","开挖"]
[13,"河源市水业集团发展有限公司","分区安装流量计工程","给水","文明路（河源大道与文明路交汇处）","5米","2025年8月26日-8月05日","开挖"]
[14,"河源市水业集团发展有限公司","新江路管道改造工程","给水","新江路","30米","2025年9月1日-9月30日","开挖"]
[15,"河源市水业集团发展有限公司","越王大道阀门更换工程","给水","越王大道","20米","2025年10月10日-10月29日","开挖"]
[16,"中国移动通信集团广东有限公司河源分公司","河源源城旺福路11#到东江盛世花园西门新建管道工程","通讯","学前路","25米","2025年7月10日-7月20日","开挖"]
[17,"中国移动通信集团广东有限公司河源分公司","河源市源城区三和小区汇聚机房配套新建管道工程","通讯","新江路（三和小区店铺前）","20米","2025年8月16日-8月20日","开挖"]
[18,"中国移动通信集团广东有限公司河源分公司","河源市源城区东发佳园汇聚机房配套新建管道工程","通讯","顺达路（东发佳园）","300米","2025年9月22日-10月22日","开挖+顶管"]
[19,"中国移动通信集团广东有限公司河源分公司","河源源城区万隆一品机房第二路由光缆整改工程","通讯","河源源城区万隆一品小区地下室出入口附近","20米","2025年11月1日-11月9日","开挖"]
[20,"河源市粤海市政工程有限公司","供水辖区内阀门更换整改","DN200阀门","城南市场路口与特产街路口交汇处",null,"7月"]
[21,"河源市粤海市政工程有限公司","供水辖区内阀门更换整改","DN400阀门","河源中学路口",null,"8月"]
[22,"中国铁塔股份有限公司河源分公司","盛源大厦新建室分项目","通讯","永安路（永安路至盛源大厦）","400米","2025年6月25日至7月25日","开挖+顶管"]
[23,"中国铁塔股份有限公司河源分公司","雅居乐花语间铁塔新建项目","通讯","文祥北路","50米","2025年7月10日至7月25日","开挖"]
[24,"新奥燃气有限公司","长提中路至大桥路市政中压燃气管道工程","燃气管线","长提中路至大桥路","570米","2025年8月30日-9月30日","开挖顶管双结合"]
[25,"新奥燃气有限公司","旺业路市政中压燃气管道工程","燃气管线","旺业路","45米","2025年7月20日-8月10日","开挖"]
[26,"新奥燃气有限公司","回头客肠粉店市政中压燃气管道工程","燃气管线","广祥路",70,"2025年7月20日-8月10日","开挖"]
[27,"新奥燃气有限公司","虾皇码头附属中压燃气管道工程","燃气管线","文星路","60米","2025年7月20日-8月10日","开挖顶管双结合"]
[]
[]
[]
[]
["注意事项：1.施工区域要具体到路段位置；\n          2.施工期限要具体到日，最长不超过3个月；\n          3.施工方式为顶管、开挖。"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}