{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":46,"n_cols":8,"rows_kept":46,"merged":[[0,0,0,7]]}
[" 2025年上半年河源中心城区城市道路挖掘计划"]
["序号","项目单位","工程名称","管线类型","具体施工区域","施工期限","施工方式","备注"]
[1,"广电网络","省干高速引线工程","通讯","永安路","2025年2月至5月","顶管"]
[2,"广电网络","省干高速引线工程","通讯","文昌路至永盛路","2025年2月至5月","顶管"]
[3,"广电网络","省干高速引线工程","通讯","越往大道（希尔顿酒店门口至立元小区跨路）","2025年2月至5月","顶管"]
[4,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年市区文星路新建铁塔项目","外电+传输","河源市源城区文星路旁绿化带","60天","顶管+人工开挖"]
[5,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年市区万隆幸福城新建铁塔项目","外电+传输","河源市源城区新港二路万隆幸福城小区门口绿化带","60天","顶管+人工开挖"]
[6,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年市区宝源一路新建铁塔项目","外电+传输","河源市源城区宝源一路与庄田路交汇处绿化带","60天","顶管+人工开挖"]
[7,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年安康花园新建铁塔项目","外电+传输","河源市源城区西环路安康花园门口绿化带","60天","顶管+人工开挖"]
[8,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年丽日广场二新建铁塔项目","外电+传输","河源市源城区沿江西路路桥头绿化带","60天","顶管+人工开挖"]
[9,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年阳光花园新建铁塔项目","外电+传输","河源市源城区沿江西路与宝源一路交接绿化带","60天","顶管+人工开挖"]
[10,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2024年威尼斯花园新建铁塔项目","外电+传输","河源市源城区沿江路威尼斯花园旁绿绿化带","60天","顶管+人工开挖"]
[11,"中国铁塔股份有限公司河源市分公司","中国铁塔广东分公司河源市分公司2025年市区华业阁新建铁塔项目","外电+传输","河源市源城区客家文化公园西侧停车场绿化带","60天","顶管+人工开挖"]
[12,"广东电网有限责任公司河源源城供电局","北郊所新建10kV永康甲线733东城中片区#7公变台区工程","供电","黄沙安置点内部路","2025/2/1-\n2025/6/30","排管"]
[13,"广东电网有限责任公司河源源城供电局","\n北郊所新建10kV福新线707东城西二片区#4公用箱变台区工程","供电","永盛路内部","2025/1/1-\n2025/6/30","排管、顶管"]
[14,"广东电网有限责任公司河源源城供电局","北郊所新建10kV大道乙线744纸袋厂#3公变台区工程","供电","源城区西二路南一巷金沟湾幼儿园旁","2025/2/1-\n2025/6/30","排管、顶管"]
[15,"广东电网有限责任公司河源源城供电局","北郊所新建10kV新江南线733上屋#2公变台区工程","供电","新江二路、供电第二小区内部\n道路","2025/2/1-\n2025/6/30","排管"]
[16,"广东电网有限责任公司河源源城供电局","北郊所新建10kV中山甲线720防保中心#2公变台区工程","供电","源城区疾病预防控制中心侧道路","2025/2/1-\n2025/6/30","排管、顶管"]
[17,"广东电网有限责任公司河源源城供电局","北郊所110kV高塘站新出一回10kV线路与10kV新地线704、10kV福新西线720环网工程","供电","文昌路、永源路、永丰路","2025/2/1-\n2025/6/30","顶管、电缆沟"]
[18,"广东电网有限责任公司河源源城供电局","北郊所110kV黄沙站10kV客家甲线709自动化改造工程","供电","万隆一品幼儿园、公园一号","2025/2/1-\n2025/6/30","排管、顶管"]
[19,"广东电网有限责任公司河源源城供电局","北郊所220kV河源站新出一回10kV线路与10kV中山甲线720、10kV中山丁线732环网工程","供电","茶山公园、新江路、丽日","2025/1/1-\n2025/6/30","排管、顶管"]
[20,"广东电网有限责任公司河源源城供电局","南郊所110kV双下站10kV石峡线717自动化改造工程","供电","迎客大道与河源大道交汇处","2025/2/1-\n2025/6/30","排管、顶管"]
[21,"广东电网有限责任公司河源源城供电局","北郊所新建10kV高民西线715丰源#5公变台区工程","供电","丰源新村(永康大道西)","2025/1/1-\n2025/6/30","排管、顶管"]
[22,"广东电网有限责任公司河源源城供电局","北郊所新建10kV新江南线733新江三路#2公变台区工程","供电","新江二路段(源城供电局附近)","\n2025/2/1-\n2025/6/30","排管"]
[23,"广东电网有限责任公司河源源城供电局","北郊所新建10kV大道乙线744源西#2公变台区工程","供电","老金沟湾农贸综合市场附近道路","2025/2/1-\n2025/6/30","排管、顶管"]
[24,"广东电网有限责任公司河源源城供电局","北郊所110kV双下站新出一回10kV线路与220kV河源站10kV新兴I线环网工程","供电","宝源二路路口至宝源桥头、宝源桥头东侧至工商银行(滨江金利公用电缆分接箱)、水宝路口至汇豪酒店北","2025/2/1-\n2025/6/30","顶管、排管"]
[25,"广东电网有限责任公司河源源城供电局","北郊所220kV河源站新出一回10kV线路与10kV红星西线739、10kV中山乙线711环网工程","供电","丽日广场北侧至丽日路对面，再沿河源大道往北至红星西路，再沿红星西路至东华路路口","2025/1/1-\n2025/6/30","顶管、排管"]
[26,"广东电网有限责任公司河源源城供电局","北郊所110kV高塘站新出一回10kV线路与10kV新院乙线734、10kV新院线704环网工程","供电","永丰路天桥南侧、人民医院西门 、文昌路永祥路路口至鸿大城北(永祥路公用电缆分接箱)","2025/1/1-\n2025/6/30","顶管、排管"]
[27,"广东电网有限责任公司河源源城供电局","北郊所新建10kV中山乙线711富景东门#2公变台区工程","供电","红星西路与新风路交叉口至富景小区里","2025/2/1-\n2025/6/30","顶管、排管"]
[28,"广东电网有限责任公司河源源城供电局","北郊所新建10kV高民西线715高塘#6公变台区工程","供电","河源大道与永康大道交界处","2025/1/1-\n2025/6/30","排管、顶管"]
[29,"广东电网有限责任公司河源源城供电局","配电部新增10kV黄沙北线706永祥路东城西片#3公变台区工程","供电","永祥路东城西片回迁点公园内","2025/2/1-\n2025/6/30","排管"]
[30,"广东电网有限责任公司河源源城供电局","北郊所新建10kV东江乙线721旺业公用#7箱变变压器台区工程","供电","旺福路","2025/2/1-\n2025/6/30","排管、顶管"]
[31,"广东电网有限责任公司河源源城供电局","北郊所新建10kV高民西线715丰源新村#8公变台区工程","供电","永康大道与丰源中路交界","2025/1/1-\n2025/6/30","排管、顶管"]
[32,"河源市水业集团发展有限公司","建设大道与中山大道交汇处流量计安装工程","供水","建设大道与中山大道交汇处","2周","明挖"]
[33,"河源市水业集团发展有限公司","长安街与中山大道交汇处流量计安装工程","供水","长安街与中山大道交汇处","3周","明挖"]
[34,"河源市水业集团发展有限公司","红星路与中山大道交汇处流量计安装工程","供水","红星路与中山大道交汇处","3周","明挖"]
[35,"河源市水业集团发展有限公司","中山大道（红星路-长安街段）DN300PVC管改造工程","供水","中山大道","3周","明挖"]
[36,"河源市水业集团发展有限公司","兴源路与中山大道交汇处流量计安装工程","供水","兴源路与中山大道交汇处","3周","明挖"]
[37,"河源市水业集团发展有限公司","益民街与中山大道交汇处流量计安装工程","供水","益民街与中山大道交汇处","3周","明挖"]
[38,"河源市水业集团发展有限公司","河源大道与文明路交汇处流量计安装工程","供水","河源大道与文明路交汇处","3周","明挖"]
[39,"河源市水业集团发展有限公司","大同路与兴源路交汇处流量计安装工程","供水","大同路与兴源路交汇处","3周","明挖"]
[40,"河源市水业集团发展有限公司","长安东路与建新街交汇处门店背后DE90-32PE管改管工程","供水","长安东路与建新街交汇处","2周","明挖"]
[41,"河源市水业集团发展有限公司","益民街财政局DE110PE管改管工程","供水","益民街","1周","明挖"]
[42,"河源市水业集团发展有限公司","建设大道市二小后门DN250排泥阀更换工程","供水","建设大道 ","2周","明挖"]
[43,"河源市水业集团发展有限公司","西环路供水应急演练工程","供水","西环路","2周","明挖"]
[44,"河源市水业集团发展有限公司","河源市公安局给水改造工程","供水","凯丰路","2周","明挖"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}